# Complete SPA Transaction Playbook – Implementation Guide

Course 4-2: SPA Mastery – Redlines, Risk Allocation & Closing Control

Case Study: JCinus Partners Capital (Buyer) acquiring Micron Technology DRAM Division (Seller) via Stock Purchase Agreement (Share Deal).

Purpose: Integrated operating system to run a transaction from term sheet through signing, closing, and post-closing monitoring.

## Package Contents

| Deliverable | File | Primary Use | Course Lessons |
| --- | --- | --- | --- |
| Deliverable 1 | README – Implementation Guide | How to deploy and operate the playbook end‑to‑end; distribution timing; workflows; role ownership. | Lessons 1–16 (Start) |
| Deliverable 2 | SPA Template with Annotated Commentary | Drafting and redlining reference; clause library mapped to risks, schedules, and workbook tabs. | Lessons 4–11 |
| Deliverable 3 | SPA Signing‑to‑Closing Control Workbook (Excel) | Control tower for hotspots, redlines, schedules, CPs, closing packs, funds flow, and post‑closing. | Lessons 12–16 (Capstone) |
| Deliverable 4 | SPA Negotiation Tactics & Closing Execution Manual | Scenario-based tactics linked to specific SPA clauses, fallbacks, and operational moves. | Lessons 12–16 |

## Operating Principles

One source of truth: the Control Workbook is the daily operating system; other documents feed it.

Traceability required: DD finding → SPA clause → Disclosure Schedule item → Indemnity/Escrow/CP → owner & deadline.

Separate commercial vs legal: escalate only commercial decisions; keep drafting mechanics with counsel.

Version control mandatory: every draft and decision is logged with timestamp and scope.

Closing is a project: CPs, consents, certificates, opinions, and funds flow are tracked like a build plan.

## Roles & Ownership (RACI)

| Workstream | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) |
| --- | --- | --- | --- | --- |
| SPA drafting & redlines | External legal (lead associate) | Buyer deal lead | In‑house legal; finance; tax | IC/Board |
| Purchase price mechanics (WC/ND/expenses) | Accounting advisor + finance | Buyer CFO/Deal lead | Seller finance; audit; tax | IC/Board |
| Disclosure schedules build | Seller in‑house legal | Seller GC | Functional owners (HR, IT, IP, Ops) | Buyer legal/deal lead |
| Indemnity/Escrow architecture | Buyer legal + deal lead | Buyer IC sponsor | R&W insurer; escrow agent; tax | Finance; integration |
| CP/Reg/Consents tracker | PMO/Deal ops | Buyer deal lead | Reg counsel; business owners | All workstreams |
| Closing pack & closing memo | External legal + deal ops | Buyer deal lead | Banks; escrow; seller counsel | IC/Board |

## How to Use the Playbook – End-to-End Workflow

| Course Window | Operational Actions (Student Outputs) |
| --- | --- |
| Lesson 1–3 (Roadmap & Setup) | Set timeline, critical path, counsel instruction letter, workstream ownership. Initialize Workbook Tabs A–D (skeleton only). |
| Lesson 4–5 (SPA structure & price) | Populate Articles I–II. Draft WC/ND adjustment definitions, peg, and dispute mechanics. Log open points in Tab A (Hotspots) and Tab B (Redline Log). |
| Lesson 6–8 (R&W, Schedules, Indemnity) | For each DD risk: map to (i) R&W, (ii) disclosure, (iii) specific indemnity, (iv) escrow/holdback, (v) RWI, (vi) CP. Track in Tabs A–C and Tab F. |
| Lesson 9–11 (Covenants, CPs, Termination) | Define interim operating controls, access rights, consents, filings, MAC/MAE, cure/waiver, drop‑dead, remedies. Track tasks in Tab D with owners/deadlines/evidence links. |
| Lesson 12–13 (Redline tactics & counsel) | Run redline rounds. Every round: export compare, update Tab B, refresh Tab A priorities, and issue a weekly Decision Packet for escalations. |
| Lesson 14–16 (Closing prep, closing day, post‑closing) | Build closing checklist and deliverables pack (Tab E), closing memo, funds flow (Tab F). After closing: true‑up, earnout, escrow releases, claims management in Tab F. |

## JCinus–Micron Scenario Inputs (Baseline Assumptions)

Transaction: 100% share acquisition of Micron DRAM Division via Delaware-law SPA; signing-to-closing gap assumed 10–24 weeks (regulatory & consents).

Base purchase price (illustrative): $4.6B; completion accounts with Target Working Capital $450M; debt-free, cash-free adjustment; transaction expenses per agreed definitions.

Key DD hotspots (illustrative): inventory reserve adequacy, customer concentration (Apple), IP/patent litigation exposure, transfer pricing/tax audits, export controls and cross-border approvals, key engineer retention.

Risk tools available: specific indemnities, special escrows, general escrow, basket/cap, R&W insurance, interim covenants, CP gating, termination rights and remedies.

Closing deliverables: bring-down certificates, board/shareholder approvals, legal opinions, good standing certificates, officer resignations, funds flow memo, escrow agreement, ancillary agreements (TSA/employment/non-compete).

## Daily/Weekly Cadence

Daily: update Tab D (CP tracker) and Tab B (redline log) for any new drafts or conditions/consents progress.

Twice weekly: 30-minute issue triage; refresh Tab A priorities; assign owners and deadlines.

Weekly: circulate Decision Packet (top open issues with options, recommendation, decision owner).

Pre-closing (T-10 to T-0): run closing rehearsal; lock closing memo; confirm bank wiring and signature authority.

## Appendix – Instruction Letter Outline (Buyer to External Counsel)

Deal summary and target structure; governing law preference; dispute forum preference.

Negotiation guardrails: basket/cap range; escrow size; survival periods; MAE position; sandbagging stance; exclusive remedy.

DD red flags and required protections (specific indemnities/escrows/CPs).

Drafting responsibilities: who drafts which schedules/exhibits; coordination with accountants and tax.

Timeline milestones: first draft date; redline rounds; signing target; CP tracking cadence; closing pack deadline.

Billing protocol: staffing expectations, budget cap, invoice detail requirements.